## Sheet1
Simple Work in Place Statement
For the Period Ending November 30_2011
ABC Contractor
Schedule of Contracts |  |  | Estimated | Estimated | Gross | Costs |  |  | Overhead | Total Cost | Prior | Estimated | Current |  |  | Total | Prior | Current |  | Over
FYE 12/31/2011 | Job | Contract | Cost to | Profit | Profit | Incurred | Percent | Estimated | Costs | Incurred | Year | Cost to | Year | Accrued | Percent | Revenue | Year | Year | Billing | (Under) | Collected
| No. | Amount | Completion | (Loss) | Percentage | To Date | Complete | Overhead | Incurred | To Date | Costs | Complete | Costs | Losses | Complete | Earned | Revenue | Revenue | To Date | Billings | To Date
Parking Deck Job | 97 | 50052 | 45709 | 4343 | 8.677% | 12889 | 28.2% | 5665 | 1597.4137 | 14486.4137 |  | 31222.5863 | 14486.4137 |  | 31.69% | 15862.8275 |  | 15862.8275 | 25026 | 9163.1725 | 23176.39
Gymnasium Job | 98 | 54615 | 51129.8 | 3485.2 | 6.381% | 26133 | 51.11% | 4809 | 2457.9325 | 28590.9325 |  | 22538.8675 | 28590.9325 |  | 55.92% | 30539.7983 |  | 30539.7983 | 43939 | 13399.2017 | 39590.65
Skating Rink Job | 99 | 135729 | 125533 | 10196 | 7.512% | 10330 | 8.229% | 11152 | 917.6883 | 11247.6883 |  | 114285.3117 | 11247.6883 |  | 8.96% | 12161.2443 |  | 12161.2443 | 72677 | 60515.7557 | 72676.62
H1 Job | 100 | 224355 | 189872 | 34483 | 15.37% | 45934 | 24.19% | 23434 | 5669.1737 | 51603.1737 |  | 138268.8263 | 51603.1737 |  | 27.18% | 60974.9202 |  | 60974.9202 | 50958 | -10016.9202 | 30795.03
H2 Job | 101 | 4295 | 3813 | 482 | 11.22% | 1264 | 33.15% | 472 | 156.4668 | 1420.4668 |  | 2392.5332 | 1420.4668 |  | 37.25% | 1600.0275 |  | 1600.0275 | 4295 | 2694.9725 | 0
H3 Job | 102 | 29874 | 26282 | 3592 | 12.02% | 20409 | 77.65% | 3251 | 2524.5285 | 22933.5285 |  | 3348.4715 | 22933.5285 |  | 87.26% | 26067.888 |  | 26067.888 | 28380 | 2312.112 | 25542.27
High School Job | 103 | 21605 | 18968 | 2637 | 12.21% | 7702.87 | 40.61% | 2346 | 952.7063 | 8655.5763 |  | 10312.4237 | 8655.5763 |  | 45.63% | 9858.9058 |  | 9858.9058 | 10803 | 944.0942 | 9722.25
Grade School Job | 104 | 74395 | 69750 | 4645 | 6.244% | 70014.55 | 100.4% | 8656 | 8656 | 78670.55 |  | -8920.55 | 78670.55 |  | 112.8% | 83909.6139 |  | 83909.6139 | 66956 | -16953.6139 | 60259.59
Church Job | 105 | 61371 | 56050 | 5321 | 8.67% | 31377 | 55.98% | 6947 | 3888.9566 | 35265.9566 |  | 20784.0434 | 35265.9566 |  | 62.92% | 38613.8631 |  | 38613.8631 | 24548 | -14065.8631 | 22154.93
Shopping Center Job | 106 | 17146 | 16150 | 996 | 5.809% | 1628.66 | 10.08% | 1396 | 140.7808 | 1769.4408 |  | 14380.5592 | 1769.4408 |  | 10.96% | 1878.5654 |  | 1878.5654 | 0 | -1878.5654 | 0
Park Job | 107 | 48543 | 44331 | 4212 | 8.677% | 36489 | 82.31% | 5494 | 4522.1305 | 41011.1305 |  | 3319.8695 | 41011.1305 |  | 92.51% | 44907.7013 |  | 44907.7013 | 43689 | -1218.7013 | 0
Total Contracts in Progress |  | 721980 | 647587.8 | 74392.2 | 10.3% | 264171.08 | 40.79% | 73622 | 31483.7778 | 295654.8578 | 0 | 351932.9422 | 295654.8578 | 0 | 45.65% | 329618.4613 | 0 | 329618.4613 | 371271 | 44895.6448 | 283917.73
ABC Contractor
Contracts Not Started |  |  | Estimated | Estimated | Gross
| Job | Contract | Cost to | Profit | Profit
| No. | Amount | Completion | (Loss) | Percentage
Water Tank Job | 108 | 19679 | 17970 | 1709 | 8.684%
Bridge Job | 109 | 8487 | 7751 | 736 | 8.672%
Parking Lot Job | 110 | 20483 | 18854 | 1629 | 7.953%
Big House Job | 111 | 8933 | 8165 | 768 | 8.597%
Small House Job | 112 | 338140 | 310885 | 27255 | 8.06%
Concrete Building Job | 113 | 550071 | 490050 | 60021 | 10.91%
Farrington Highway Job | 114 | 86879 | 79431 | 7448 | 8.573%
Waianae Job | 115 | 415190 | 383899 | 31291 | 7.537%
Total Contracts Not Started |  | 1447862 | 1317005 | 130857 | 9.038%